## In-Depth
| Month 1 |  |  |  | Month 2 |  |  |  | Month 3
Activities | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11
PREP CHECKLIST: Collect the following...
Domain name registrar sign-in
Website host server contact
Analytics tracking code
Search engine webmaster confirmation codes
PPC conversion tracking code (if doing PPC campaign)
Company logo in a vector format
Branding guidelines and sample collateral
All images, graphics and downloadable files (PDFs)
DISCOVERY: Define or identify the following...
Buyer personas
Website objectives
Desired visitor perception of site
Calls to action
Color palette
Features and functionality
Page layouts (home and interior/product)
Graphic sitemap
Main and secondary navigation options
Content audit
DESIGN & STRUCTURE: Complete the following...
Creative brief (submit to web team)
Design concept 1 (web team)
Design concept 1 feedback
Design concept 2 (web team)
Design concept 2 feedback
Design signoff
Wrap design around CMS platform (web team)
Content & OPTIMIZATION: Create the following...
Keyword map
Define tone and style of content
Create Content Sheets
Identify content author
Create new page content
Optimize all pages
Link body content to referenced or related pages
Proof all content
BUILD OUT & Q.A.: Complete the following...
Find every page on the existing website that Google has indexed.
Develop a 301 Redirect Chart
Submit 301 Redirect Chart to web team
Learn how to use the new CMS platform
Create Upload Cheat Sheet
Create all pages in the CMS and organize according to sitemap
Upload all image and graphics into the CMS
Upload all content into the pages
Perform a quality assurance test
LAUNCH: Complete the following...
Instruct original Web Host Server to point A Record to new website host server IP Address
Alert web team that this change has been made
Test all 301 redirects
Verify the site in all search engine webmaster centrals
Sumbit new XML sitemap into each serach engine webmaster central
Verify all analytics tracking codes are installed properly
Review for any crawl errors on Google Webmaster Tools (48 hours after launch)
Create a new 301 Redirect Chart for all pages not found by Google and other search engines. Submit to web team.